## Data Entry
Quality Tools
Gantt Chart
Description
Gantt Chart
This template illustrates a Gantt Chart, also called a Milestone Chart, Project Bar Chart or Activity Chart. A detailed discussion of Gantt Charts can be found at www.ASQ.org
Learn About Gantt Charts
Instructions
| ● | Enter up to 30 tasks in the cells provided
| ● | Enter the Start Date for each task and the number of days to complete it.
| ● | Enter the Pecent Complete for each task.
Learn More
To learn more about other quality tools, visit the ASQ Learn About Quality web site.
Learn About Quality
|  | Task | Start Date | # Days Required | Percent Complete | Task | Start Date | # Days Required | Percent Complete
|  | Develop broad plan | 2007-04-03 | 14 | 100
|  | Present plan to council | 2007-04-20 | 3 | 100
|  | Identify team | 2007-04-20 | 30 | 100
|  | Train team | 2007-05-20 | 7 | 100
|  | Develop detailed plan | 2007-05-27 | 7 | 100
|  | Conduct preliminary research | 2007-05-25 | 14 | 100
|  | Identify key practices | 2007-06-07 | 7 | 100
|  | Identify benchmark partners | 2007-05-25 | 40 | 25
|  | Collect public data | 2007-06-10 | 21 | 50
|  | Analyze public data | 2007-07-01 | 21 | 0
|  | Identify current state | 2007-06-15 | 28 | 0
|  | Develop benchmark questions | 2007-06-15 | 7 | 0
|  | Visit benchmark partners | 2007-07-15 | 28 | 0
|  | Develop new process | 2007-07-28 | 35 | 0
|  | Present new plan to council | 2007-08-31 | 3 | 0

## Calculations (hidden)
Task | Start Date | # Days Required | % Complete | Days Comp | Days Incomp
Develop broad plan | 2007-04-03 | 14 | 100 | 14 | 0
Present plan to council | 2007-04-20 | 3 | 100 | 3 | 0
Identify team | 2007-04-20 | 30 | 100 | 30 | 0
Train team | 2007-05-20 | 7 | 100 | 7 | 0
Develop detailed plan | 2007-05-27 | 7 | 100 | 7 | 0
Conduct preliminary research | 2007-05-25 | 14 | 100 | 14 | 0
Identify key practices | 2007-06-07 | 7 | 100 | 7 | 0
Identify benchmark partners | 2007-05-25 | 40 | 25 | 10 | 30
Collect public data | 2007-06-10 | 21 | 50 | 10.5 | 10.5
Analyze public data | 2007-07-01 | 21 | 0 | 0 | 21
Identify current state | 2007-06-15 | 28 | 0 | 0 | 28
Develop benchmark questions | 2007-06-15 | 7 | 0 | 0 | 7
Visit benchmark partners | 2007-07-15 | 28 | 0 | 0 | 28
Develop new process | 2007-07-28 | 35 | 0 | 0 | 35
Present new plan to council | 2007-08-31 | 3 | 0 | 0 | 3

## About This Template
This template was written for the American Society for Quality by
Stat Aids
Your feedback is welcome and encouraged. Please e-mail to:
Stat_Aids@yahoo.com